## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | D.S.; 2/24
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | D.S.; 2/24
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | D.S.; 2/24
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | D.S.; 2/24
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | D.S.; 2/24
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | D.S.; 2/24
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | D.S.; 2/24
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | J.S.; 2/27
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | J.S.; 2/27
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | J.S.; 2/27
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | J.S.; 2/27
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | J.S.; 2/27
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | J.S.; 2/27
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | J.S.; 2/27
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | J.S.; 2/27
As a player I want to move my pieces so that I can play a game of checkers | Given it is my turn, When I pick up a piece, Then the valid spaces I can place it should be highlighted.
Given I have picked up one of my basic pieces When I try to drop it in an empty black space one space forward(away from my side of the board) and to the left, or one space forward and to the right, Then the piece should move to that space.
Given I have picked up one of my basic pieces When I try to drop it in any space more than one space away from it Then that piece should return to it’s original space and a message should appear that tells me that was an invalid move.
Given I have picked up one of my basic pieces When I try to drop it in any space behind its current position (closer to my side of the board) Then that piece should return to its original space and a message should appear that tells me that was an invalid move.
Given I have picked up one of my king pieces When I try to drop it in an empty black space one space forward and to the left, one space forward and to the right, one space back and to the left, or one space back and to the right, Then the piece should stay there.
Given I have picked up one of my king pieces When I try to drop it in any space more than one space away, or in any white space, Then that piece should return to it’s original space and a message should appear that tells me that was an invalid move.
Given I have made a valid move I want to keep When I press the `submit turn` button, Then that move will be seen my myself and my opponent
Given I have made a valid move I do not want to keep want to keep When I press the `Backup` button, Then the piece will move back to the space it came from.
Given I have not yet made a move, then If I hit the `submit turn` button or the `backup` button then nothing should happen.
As a player I want to Resign so that I can leave the game. | Given that it is my turn when I decide I want to resign then I expect to see a button I can click to do so.
Given that I decided to resign when I click the button to resign then I expect to see a warning/confirmation about that decision.
Given that I am sure I want to resign when I click on the confirmation then I expect the game to end.
Given that it is not my turn when my opponent decides to resign then I expect the game to end.
As a Player I want the Game to end so that I know when there is a winner. | Given it is my turn when I capture my opponents last piece then I expect the game to be over.
Given it is not my turn when my opponent captures my last piece then I expect the game to be over.
Given it is my turn when I am unable to make a move then I expect the game to be over.
Given it is not my turn when my opponent is unable to make a move then I expect the game to be over.
Given it is my turn when I resign then I expect the game to be over.
Given it is not my turn when my opponent resigns then I expect the game to be over.
As a _PLAYER_ I want to _KNOW WHEN IT'S MY TURN_ so that _I CAN MAKE A MOVE_. | Given it is my turn when I make a valid move then I can no longer move, and it is the other player's turn. |  |  | Pass | E.S; 4/5
Given it is my turn when I make an invalid move then I can still move, and it is still my turn.
Given it is not my turn when the other player makes a valid move then I can move, and it is my turn.
Given it is not my turn when the other player makes an invalid move then I still cannot move, and it is not my turn.
As a _PLAYER_ I want to _JUMP MY OPPONENT'S PIECES_ so that _I CAN CAPTURE THEM_. | Given that a space adjacent to my piece has an opponent piece followed by an empty square when I move over the opponent to the empty square then I capture the opponent's piece.
Given that a space adjacent to my piece has an opponent piece followed by an empty square, when it is my turn then the jump space will be highlighted with the other spaces.
As a _PLAYER_ I want to _KING MY PIECE_ so that _I CAN HAVE A STRONGER PIECE_. | Given my piece reached the row of the board furthest away from me when I completed a jump or move then my piece becomes a king.
Given I placed a second piece on top of an opponent's king piece when I completed a jump or move then I crowned the opponent's king piece.
Given my piece is king when it is my turn then It can move and jump diagonally backward toward me.
Given my piece is king when it is my turn then It can move and jump diagonally forward away from me.
Given my piece is king when I'm doing a multiple jump move then the jumps can be any combination of forward or backward jumps.
Given my piece is king when multiple jumps are available then I can choose among them.
As a User I want to be able to start a replay in a game window so I can view a game as if I was playing it. | Given I want to watch a replay of a game when I click the `replays` button on the home screen then `I will see a list of watchable games.
Given I am looking at a list of watchable games when I want to find a specific game then I can expect to find them in chronological order.
Given I want to watch a specific game when I click the game ID of the game I want to watch then I expect to be able to watch the game I clicked on.
Given that I want to watch a replay of the game when I start watching the one I select then the original players names should be displayed.
Given that I want to watch a replay of the game when I start watching the one I select then the board should not update until I press a control button.
Given that I am watching a game when click the `swap view` button then to be able to see the board from the other player's perspective.
As a User I want to be able to press the forward button to advance a move in a replay | Given I am watching a checkers game replay when I press the next button then I will be able to see the next player turn taken.
Given I am watching a checkers game replay when I am on the last turn of a replay then the next button will be disabled.
As a User I want to be able to back up to a previous move | Given I am watching a checkers game replay when I press the previous button then I will see the previous player turn taken.
Given I am watching a checkers game replay when I am on the first turn of a replay then the previous button will be disabled.
As a User I want to be able to exit a replay so that I can do something else with my life. | Given I am watching a checkers game replay when I press the exit button then I will be returned to the replay menu.
As User, I want Press a play button so that the game will continue automatically. | Given I am looking at a replay of a game when I press the play button then the game will continue automatically.
As a Player I want to see the current turn # so that I can tell where I am in the game. | Given I want to watch a replay of a game when I start watching then I expect to see the current/total # of turns displayed.
Given I am watching a replay of a game when I start click on the current turn display then I expect to be able to enter the number of the turn I wish to go to.